## Plan
Planned creation date | HMRC Load status | Load date | Load notes | Jersey / Guernsey status | DIT Production status | Envelope ID | Contains balances from | Content | Creation Scripting | Import scripting
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 18041 | 2018-12-13 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 18042 | 2018-12-14 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 18043 | 2018-12-17 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 18044 | 2018-12-18 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 18045 | 2018-12-19 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 18046 | 2018-12-20 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 18047 | 2018-12-21 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 18048 | 2018-12-26 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 18049 | 2018-12-27 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 18050 | 2018-12-28 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 18051 | 2019-12-31 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19001 | 2019-01-03 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19002 | 2019-01-04 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19003 | 2019-01-07 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19004 | 2019-01-08 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19005 | 2019-01-09 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19006 | 2019-01-10 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19007 | 2019-01-11 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19008 | 2019-01-14 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19009 | 2019-01-15 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19010 | 2019-01-16 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19011 | 2019-01-17 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19012 | 2019-01-18 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19013 | 2019-01-21 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19014 | 2019-01-22 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19015 | 2019-01-23 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19016 | 2019-01-24 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19017 | 2019-01-25 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19018 | 2019-01-28 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19019 | 2019-01-29 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19020 | 2019-01-30 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19021 | 2019-02-01 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19022 | 2019-02-04 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19023 | 2019-02-05 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19024 | 2019-02-06 | EU data only | n/a | n/a
n/a | Loaded - EU data only | 2019-03-28 |  | Loaded | Loaded | 19025 | 2019-02-07 | EU data only | n/a | n/a
2019-03-28 | Loaded | 2019-03-29 | Issues with certificates having already been pre-loaded; decision taken to proceed as issue is non-impacting and data will be required for Jersey and Guernsey |  | Loaded | 19026 | 2019-02-08 | All reference data types updates, inclusive of: - certificate types - footnote types - additional code types - measure types - base regulations - geographical area renames - certificates | Reference data generation scripts | python3 convert.py TGB19026.xml base_regulations_complete.xml geographical_areas.xml measure_types.xml addition al_code_types.xml footnote_types.xml certificate_types.xml certificates.xml
2019-03-28 | Loaded |  |  |  | Loaded | 19027 | 2019-02-11 | Kill all unnecessary Trade Remedies | python3 bulk_migrate.py trade_remedies3 | python3 convert.py TGB19027.xml regulation_end_trade_remedies3_2019-03-28.xml
2019-03-28 | Loaded |  |  |  | Loaded | 19028 | 2019-02-12 | Port all maintained Trade Remedies - part 1 | python3 migrate_measures.py r r trade_remedies3 | python3 convert.py TGB19028.xml -p trade_remedies_insert01.txt
2019-03-28 | Loaded |  |  |  | Loaded | 19029 | 2019-02-13 | Port all maintained Trade Remedies - part 2 | python3 migrate_measures.py r r trade_remedies4 | python3 convert.py TGB19029.xml -p trade_remedies_insert02.txt
2019-03-28 | Loaded | 2019-03-30 | No issues |  | Loaded | 19030 | 2019-02-14 | Port or delete all ancillary measures - Supplementary units - Credibility checks - Surveillance measures | python3 migrate_measures.py m t cred N1234567 python3 migrate_measures.py m r supp I1900010 python3 migrate_measures.py m t cred N1234567 | python3 convert.py TGB19030.xml measuretypes_end_cred_2019-03-28.xml measuretypes_end_supp_new_regulation_I1900010_2019-03-28.xml measuretypes_end_surv_2019-03-28.xml
2019-03-28 | Loaded | 2019-03-30 | No issues |  | Loaded | 19031 | 2019-02-15 | Kill all quota definitions | python3 kill_all_quota_definitions.py | python3 convert.py TGB19031.xml kill_quota_definitions.xml
2019-03-28 | Loaded | 2019-03-30 | XML issue - xifed |  | Loaded | 19032 | 2019-02-18 | Kill all quota measures | python3 migrate_measures.py m t wto_quotas N1234567 | python3 convert.py TGB19032.xml measuretypes_end_wto_quotas_2019-03-28.xml
2019-03-28 | Loaded | 2019-03-30 | No issues |  | Loaded | 19033 | 2019-02-19 | Kill multiple Free Trade Agreements, including: - Mexico - Jordan - Moldova - Montenegro - Macedonia - South Africa - SADC - South Korea - Andorra - Syria - Subcontinent - Cape Verde - seem to be no measures | python3 migrate_measures.py c t mexico N1234567 python3 migrate_measures.py c t jordan N1234567 python3 migrate_measures.py c t moldova N1234567 python3 migrate_measures.py c t montenegro N1234567 python3 migrate_measures.py c t macedonia N1234567 python3 migrate_measures.py c t southafrica N1234567 python3 migrate_measures.py c t sadc N1234567 python3 migrate_measures.py c t southkorea N1234567 python3 migrate_measures.py c t andorra N1234567 python3 migrate_measures.py c t syria N1234567 python3 migrate_measures.py c t subcontinent N1234567 | python3 convert.py TGB19033.xml mexico.xml jordan.xml moldova.xml montenegro.xml macedonia.xml southafrica.xml sadc.xml southkorea.xml andorra.xml syria.xml subcontinent.xml
2019-03-28 | Loaded | 2019-03-30 | No issues |  | Loaded | 19034 | 2019-02-20 | Kill multiple Free Trade Agreements, including: - Algeria - Serbia - Albania - Bosnia - Egypt - Georgia - Ghana - Kosovo | python3 migrate_measures.py c t algeria N1234567 python3 migrate_measures.py c t serbia N1234567 python3 migrate_measures.py c t albania N1234567 python3 migrate_measures.py c t bosnia N1234567 python3 migrate_measures.py c t egypt N1234567 python3 migrate_measures.py c t georgia N1234567 python3 migrate_measures.py c t ghana N1234567 python3 migrate_measures.py c t kosovo N1234567 | python3 convert.py TGB19034.xml algeria.xml serbia.xml albania.xml bosnia.xml egypt.xml georgia.xml ghana.xml kosovo.xml
2019-03-28 | Loaded | 2019-04-03 | Issues found - see load report / fixed |  |  | 19035 | 2019-02-21 | Kill multiple Free Trade Agreements, including: - Tunisia - Liechtenstein - San Marino - Turkey - Ukraine - Cameroon - Japan | python3 migrate_measures.py c t tunisia N1234567 python3 migrate_measures.py c t liechtenstein N1234567 python3 migrate_measures.py c t sanmarino N1234567 python3 migrate_measures.py c t turkey N1234567 python3 migrate_measures.py c t ukraine N1234567 python3 migrate_measures.py c t cameroon N1234567 python3 migrate_measures.py c t japan N1234567 | python3 convert.py TGB19035.xml tunisia.xml liechtenstein.xml sanmarino.xml turkey.xml ukraine.xml cameroon.xml japan.xml
2019-03-28 | Loaded | 2019-04-04 | No issues |  |  | 19036 | 2019-02-22 | UK-specific commodity codes | python3 commodities.py | python3 convert.py TGB19036.xml goods_nomenclature.xml
2019-03-28 | Loaded | 2019-04-04 | No issues |  |  | 19037 | 2019-02-25 | Kill all MFNs | python3 migrate_measures.py m t mfn N1234567 | python3 convert.py TGB19037.xml measuretypes_end_mfn_2019-04-03.xml
2019-04-02 | Loaded | 2019-04-04 | No issues |  |  | 19038 | 2019-02-26 | Kill Multiple Free Trade Agreements, including: - Canada & Canada re-imports - Morocco - Lebanon | python3 migrate_measures.py c t canada N1234567 python3 migrate_measures.py c t ca_imports N1234567 python3 migrate_measures.py c t morocco N1234567 python3 migrate_measures.py c t lebanon N1234567 | python3 convert.py TGB19038.xml canada.xml ca_imports.xml lebanon.xml morocco.xml
2019-04-02 | Loaded | 2019-04-05 | Issues found - see load report / fixed |  |  | 19039 | 2019-02-27 | Kill Multiple Free Trade Agreements, including: - Central America - Nicaragua - Panama - Honduras - Guatemala - Costa Rica - El Salvador | python3 migrate_measures.py c t centralamerica N1234567 python3 migrate_measures.py c t nicaragua N1234567 python3 migrate_measures.py c t panama N1234567 python3 migrate_measures.py c t guatemala N1234567 python3 migrate_measures.py c t honduras N1234567 python3 migrate_measures.py c t costarica N1234567 python3 migrate_measures.py c t elsalvador N1234567 | python3 convert.py TGB19039.xml centralamerica.xml nicaragua.xml panama.xml guatemala.xml honduras.xml costarica.xml elsalvador.xml
2019-04-02 | Loaded | 2019-04-05 | No issues |  |  | 19040 | 2019-02-28 | Kill suspensions | python3 migrate_measures.py m t susp | python3 convert.py TGB19040.xml measuretypes_end_susp_2019-04-03.xml
2019-04-02 | Loaded | 2019-04-05 | No issues |  |  | 19041 | 2019-03-01 | Load ESA, Palestine and Pacific, Cariforum | python3 migrate_measures.py c r palestine P1900110 python3 migrate_measures.py c r esa P1900060 python3 migrate_measures.py c r cariforum P1900050 python3 migrate_measures.py c r pacific P1900080 | python3 convert.py TGB19041.xml palestine.xml esa.xml cariforum.xml pacific.xml
2019-04-02 | Loaded | 2019-04-05 | No issues |  |  | 19042 | 2019-03-04 | End old GSP measures (erroneously missed R120978) GSP part 1 | python3 base_regulations.py gsp python3 migrate_measures.py r t R120978 python3 gsp.py 2020 | python3 convert.py TGB19042.xml reg_gsp.xml regulation_end_R120978_2019-04-10.xml gsp_2020.xml
2019-04-02 | Loaded | 2019-04-05 | No issues |  |  | 19043 | 2019-03-05 | GSP part 2 | python3 gsp.py 2027 | python3 convert.py TGB19043.xml gsp_2027.xml
2019-04-02 | Loaded | 2019-04-05 | No issues |  |  | 19044 | 2019-03-06 | GSP part 3 | python3 gsp.py 2005 | python3 convert.py TGB19044.xml gsp_2005.xml
2019-04-02 | Loaded | 2019-04-05 | No issues |  |  | 19045 | 2019-03-07 | Transitional Protection Measure | python3 gsp.py 1032 | python3 convert.py TGB19045.xml gsp_1032.xml
2019-04-05 | Loaded | 2019-04-06 | No issues |  |  | 19046 | 2019-03-08 | Load reliefs | python3 generic_measure.py pharma python3 generic_measure.py registered_aircraft python3 generic_measure.py certain_aircraft python3 generic_measure.py vessels_platform python3 generic_measure.py authorised_release_relief | python3 convert.py TGB19046.xml pharma.xml registered_aircraft.xml certain_aircraft.xml vessels_platform.xml authorised_release_relief.xml | SKIP | python3 convert.py TGB19046.xml
2019-04-05 | Loaded | 2019-04-06 | No issues |  |  | 19047 | 2019-03-11 | Load WTO quotas | python3 create_quotas.py wto10 | python3 convert.py TGB19047.xml quotas_wto10.xml | SKIP | python3 convert.py TGB19047.xml
2019-04-05 | Loaded | 2019-04-06 | No issues |  |  | 19048 | 2019-03-12 | All MFNs | python3 mfn_load.py | python3 convert.py TGB19048.xml mfn.xml
2019-04-05 | Loaded | 2019-04-06 | No issues |  |  | 19049 | 2019-03-13 | Load measures only for continued Trade Agreements: - Switzerland - Switzerland re-imports measures - Faroes - Israel - Andean - South Korea | python3 migrate_measures.py c r ch_imports P1900031 python3 migrate_measures.py c r switzerland P1900030 python3 migrate_measures.py c r faroeislands P1900220 python3 migrate_measures.py c r israel P1900100 python3 migrate_measures.py c r andean P1900230 python3 migrate_measures.py c r southkorea P1900020 | python3 convert.py TGB19049.xml ch_imports.xml switzerland.xml faroeislands.xml israel.xml andean.xml southkorea.xml
2019-04-06 | Loaded | 2019-04-07 |  |  |  | 19050 | 2019-03-14 | Geographical area membership updates | python3 memberships.py | python3 convert.py TGB19050.xml memberships.xml
2019-04-06 | Loaded | 2019-04-07 |  |  |  | 19051 | 2019-03-15 | EU Import & export control - tranche 1 [close] | python3 bulk_migrate.py impex01 | python3 convert.py TGB19051.xml -p impex01.txt | SKIP | python3 convert.py TGB19051.xml
2019-04-06 | Loaded | 2019-04-07 |  |  |  | 19052 | 2019-03-18 | EU Import & export control - tranche 2 [close] | python3 bulk_migrate.py impex02 | python3 convert.py TGB19052.xml -p impex02.txt | SKIP | python3 convert.py TGB19052.xml
2019-04-06 | Loaded | 2019-04-07 |  |  |  | 19053 | 2019-03-19 | EU Import & export control - tranche 3 [close] | python3 bulk_migrate.py impex03 | python3 convert.py TGB19053.xml -p impex03.txt | SKIP | python3 convert.py TGB19053.xml
2019-04-06 | Loaded | 2019-04-07 |  |  |  | 19054 | 2019-03-20 | EU Import & export control - tranche 4 [close] | python3 bulk_migrate.py impex04 | python3 convert.py TGB19054.xml -p impex04.txt | SKIP | python3 convert.py TGB19054.xml
2019-04-06 | Loaded | 2019-04-07 |  |  |  | 19055 | 2019-03-21 | Load Chile measures Load quotas for : - Israel - Switzerland - Andean - Faroes - Norway - Iceland - ESA | python3 migrate_measures.py c r chile P1900090 python3 create_quotas.py ftas | python3 convert.py TGB19055.xml chile.xml quotas_ftas.xml |  | python3 convert.py TGB19055.xml quotas_ftas.xml
2019-04-06 | Loaded | 2019-04-07 |  |  |  | 19056 | 2019-03-22 | Reinstate UK impex measure - tranche 1 | python3 bulk_migrate.py impex01 | python3 convert.py TGB19056.xml -p impex01b.txt | SKIP | python3 convert.py TGB19056.xml
2019-04-06 | Loaded | 2019-04-07 |  |  |  | 19057 | 2019-03-25 | Reinstate UK impex measure - tranche 2 | python3 bulk_migrate.py impex02 | python3 convert.py TGB19057.xml -p impex02b.txt | SKIP | python3 convert.py TGB19057.xml
2019-04-06 | Loaded | 2019-04-07 |  |  |  | 19058 | 2019-03-26 | Reinstate UK impex measure - tranche 3 | python3 bulk_migrate.py impex03 | python3 convert.py TGB19058.xml -p impex03b.txt | SKIP | python3 convert.py TGB19058.xml
2019-04-06 | Loaded | 2019-04-07 |  |  |  | 19059 | 2019-03-27 | Reinstate UK impex measure - tranche 4 | python3 bulk_migrate.py impex04 | python3 convert.py TGB19059.xml -p impex04b.txt | SKIP | python3 convert.py TGB19059.xml
2019-04-07 | [5 empty] | 19060 | 2019-03-28 | UK-specific Import and export controls | python3 pandr.py | python3 convert.py TGB19060.xml national_pandr.xml
[6 empty] | 19061 | 2019-03-29 | End date Ceuta & Melilla preferences End Turkey anti-dumping control End representative price measures Migrate Overseas territories measures End date Samoa measures | python3 migrate_measures.py c t ceutamelilla N1234567 python3 migrate_measures.py r t D9601429 python3 migrate_measures.py m t 489 N1234567 python3 base_regulations.py oct python3 migrate_measures.py c r overseas_territories P1900410 python3 migrate_measures.py c t samoa N1234567 | python3 convert.py TGB19061.xml ceutamelilla.xml regulation_end_D9601429_2019-04-10.xml measuretypes_end_489_2019-04-10.xml base_regulations_trade_oct.xml overseas_territories.xml samoa.xml
[6 empty] | 19062 | 2019-04-01 | WTO Quotas | python3 create_quotas.py wto10 | python3 convert.py TGB19062.xml quotas_wto10.xml
[6 empty] | 19063 | 2019-04-02
[6 empty] | 19064 | 2019-04-03 | Load Norway and Iceland measures (not quotas)
[6 empty] | 19065 | 2019-04-04 | Quota associations
[6 empty] | 19066 | 2019-04-05 | Keep clear for data fixes
Load safeguard measures & Byrd measures
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Bold means we have the incremental data file from EU / HMRC
Note on J54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to include the base regulations for GSP into the main regulation list Also need to check that GSP now increments